ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	8

5.	LOGISTICS AND TIMING	8

5.1.	Location	8

5.2.	Start date & Period of implementation of tasks	9

6.	REQUIREMENTS	9

6.1.	Staff	9

6.2.	Office accommodation	9

6.3.	Facilities to be provided by the Contractor	9

6.4.	Equipment	9

7.	REPORTS	10

7.1.	Reporting requirements	10

7.2.	Submission and approval of reports	10

8.	MONITORING AND EVALUATION	10

8.1.	Definition of indicators	10

8.2.	Special requirements	10

# BACKGROUND INFORMATION

## Partner country

Republic of Bulgaria and Republic of Serbia.

## Contracting Authority

## International Business School, Republic of Bulgaria

## Country background

The IPA II CBC Programme Bulgaria – Serbia overall aim is to stimulate the balanced and sustainable development of the Bulgaria – Serbia border region integrated in the European space – achieved through smart economic growth. The project “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people” complies with the specific objective related to priority axis 2, namely - Investing in youth, education and skills.

The project background originates from the renowned educational institutions on all levels: elementary, secondary and universities in Botevgrad and Vranje, high rate of unemployment (>15% in Vranje and ~9% in Botevgard) and lack of required skills on the labour market.

The project is highly focused on entrepreneurial learning introduction into the formal education, encompassing elementary, secondary and university schools. The aim is to strengthen employment and economic potential of the youth, contributing thereby to economic growth in the region.

The project is financed by the INTERREG IPA CBC Bulgaria – Serbia Programme and will be implemented in the period 23rd November 2016 – 22nd February 2018 in partnership with College of Applied Professional Studies, Vranje, Serbia.

## Current situation in the sector

- International Business School, as a Lead project partner is responsible for smooth management of the project and for implementation of the activities on the Bulgarian territory, as well as participation of Bulgarian part in activities on Serbian territory. One of the main tasks of the International Business School in terms of project management includes conduction of tender procedures for planned expenditures.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective of the contract is providing services for organisation of events and accommodation, incl. transport related to implementation of Project No. CB007.1.21.159: “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”; Priority Axis: Youth; Specific Objective 2.1 Skills and Entrepreneurship; Type of project: Soft, financed by the European Union, in accordance with the rules of Interreg – IPA CBC Bulgaria – Serbia Programme CCI Number 2014TC16I5CB007.

## Purpose

The purpose of this contract is as follows:

The purpose of this contract is to provide and coordinate professional and timely services for successful organization of several events, incl. rent of halls, rent of microphones and speakers, video projector and canvas, refreshment and catering, accommodation for project team members and participants in the events, transportation provided by rented buses.

## Results to be achieved by the Contractor

The Contractor should successfully organize all detail listed services in section 4, according to the specific requirements detailed in the same section of this document and should submit the required report, described in section 7.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear understanding of the contract objectives and purposes by the Contractor;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation.

## Risks

Potential risks to the successful implementation of the contract include:

- Lack of communication and logistical coordination between the Contractor and the Contracting Authority. In order to avoid this risk, the Contractor should show initiative and maintain continuous contact with the relevant representatives of the Contracting Authority.

- Insufficient quality of the services provided by the Contractor experts and suppliers. In order to avoid this risk the Contractor should use the most reliable and experienced staff/service providers on its disposal.

# SCOPE OF THE WORK

## General

### Description of the assignment

The aim of this contract is necessary services and overall logistical coordination for the organization of the events, accommodation of team members and participants and transport mentioned in p. 2.2 to be provided by the Contractor. The Contractor will have to provide a variety of professional services, such as rent of hall, rent of audio/video equipment, catering services, accommodation for participants and team members, preparation consumables for events, etc.

### Geographical area to be covered

Botevgrad, Republic of Bulgaria and Vranje, Republic of Serbia

### Target groups

- Expert staff involved in project implementation;

- Participants in project events – students and teachers from elementary, secondary and university schools, and parents of students;

- Educational institutions;

- Visitors to project events;

- Representatives of the national and regional media;

- Local community members in the cross-border region where the project partners are located;

## Specific work

- This section individually describes the specific services to be provided by the Contractor within the implementation of project “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”. The Contractor should coordinate and receive prior approval from the Contracting Authority regarding important issues related to the organization of the events such as venue, equipment, menu, training materials, logistics, accommodation, transportation, etc.

- Rent of halls for following events:

- For 1-day Cooperation with parents event for 430 participants:

- A formal conference hall, preferably at a central location, in Botevgrad, Bulgaria;

- The premises should be rented for the whole duration of the event;

- Conference hall capacity: minimum 430 people;

- In addition to the conference hall, a separate hall/lobby should be reserved in the same location for catering;

- The space for catering should be enough to accommodate all conference participants during coffee and lunch breaks.

- For 1- day BOND Conclusion event for 245 participants:

- A formal conference hall, preferably at a central location, in Botevgrad, Bulgaria;

- The premises should be rented for the whole duration of the event;

- Conference hall capacity: minimum 245 people;

- In addition to the conference hall, a separate hall/lobby should be reserved in the same location for catering;

- The space for catering should be enough to accommodate all conference participants during coffee and lunch breaks.

- Rent of audio/video equipment for following events:

- For 1-day Cooperation with parents event for 430 participants:

- Multimedia projector and screen, appropriate in size and with technical specifications suitable for the type and venue of the event;

- Microphone;

- Speakers;

- For 1- day BOND Conclusion event for 245 participants:

- Multimedia projector and screen, appropriate in size and with technical specifications suitable for the type and venue of the event;

- Microphone;

- Speakers;

Catering services provided for the following events:

- 3-day entrepreneurial learning programme development session – 35 persons;

- 1-day Joint Classes Day for elementary schools – 141 persons;

- 1-day Joint Classes Day for secondary schools – 67 persons;

- 1-day Cooperation with parents event - 422 participants

- 5-days Entrepreneurial learning curricula session – 35 persons

- 1- day BOND Conclusion event - 237 participants

For every of the above listed events the Contractor should provide two coffee breaks (one in the morning and one in the afternoon), beverages and one lunch break.

Coffee break requirements

- To be served during the registration, at the beginning of the event;

- To be consisted of – for each guest:

- 1 cup of freshly brewed coffee or tea;

- 1 small bottle of mineral water (500 ml);

- 1 small bottle/can of soft drink (minimum 300 ml);

- Freshly baked cookies and sweets: minimum 4 pieces per person.

- The catering services should include professional staff for serving.

Catering during lunch break requirements

- Buffet style;

- The catering should comprise the following items for each guest:

-1 cup of coffee or tea;

-1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml);

-At least 5 serving pieces of warm cocktail snacks, including vegetarian options;

-At least 5 serving pieces of cold cocktail snacks, including vegetarian options;

-At least 4 pieces of cocktail desserts;

-At least 1 fresh fruit;

- The Contractor should prepare at least 3 versions of the lunch menu. The menus should be sent by the Contractor to the Contracting Authority for approval at least 5 working days prior to the meeting.

- The catering services should include professional staff for serving of the cocktail drinks and snacks;

- Sufficient cocktail tables should be set at the business lunch for the entire duration of the lunch break.

- Refreshment provided for 7 university students for 2 weeks:

- Total of 14 refreshments provided for the university students visiting elementary and secondary schools – 1 coffee/tea and a bottle of mineral water (500ml) a day;

- Transportation:

- The Contractor has to provide rented buses, drivers and organize the transportation of the participants in the following events:

- 2 buses for 113 Bulgarian participants to/from the BOND outset event in Vranje, Serbia – 2 buses x 2 directions x 245km;

- 1 bus for local travels of 13 teachers for the 3-day session in Botevgrad, Bulgaria – 50km;

- 1 bus for travel of 23 participants to/from 3-day session in Vranje, Serbia - 1 bus x 4 directions x 245km;

- 1 bus for travel of 23 participants to/from 1-day Joint Classes day in Vranje, Serbia - 1 bus x 2 directions x 245km;

- 1 bus for travel of 23 participants to/from 3-day session in Vranje, Serbia - 1 bus x 4 directions x 245km;

- 1 bus for local travels of max. 203 participants of 1-day Cooperation with parents event in Botevgrad, Bulgaria – 70km;

- Sufficient busses to transport 203 participants to/from the 1-day Students BOND Day in Vranje, Serbia - 4 buses x 2 directions x 245km = 1960km;

- 1 bus for travels of 14 participants to/from the 5-day session in Vranje, Serbia - 1 bus x 4 directions x 245km;

- 1 bus for local travels of max. 113 participants for Closing event in Botevgrad, Bulgaria – 65km;

- N.B.!!!! For the events that last more than one day, the buses will be returning to original start point, so one travel will have two directions.

- Accommodation for participants in the following events:

- 3-day “Train-the-Trainer”programme elaboration event in Vranje, Serbia

- accommodation of 23 participants staying in Vranje for 3 nights in a 2 or 3 star hotel (single rooms, including breakfast);

- 3-day Exchange of practice event in Vranje, Serbia

- accommodation of 23 participants staying in Vranje for 3 nights in a 2 or 3 star hotel (single rooms, including breakfast);

- 5-day Development of the models for the new “Train-the-Trainer” curricula event in Vranje, Serbia

- accommodation of 14 participants staying in Vranje for 5 nights in a 2 or 3 star hotel (single rooms, including breakfast).

- Accommodation for project team members:

- 3-day “Train-the-Trainer”programme elaboration event in Vranje, Serbia

- accommodation of 3 project team members staying in Vranje for 3 nights in a 2 or 3 star hotel (single rooms, including breakfast);

- 3-day Exchange of practice event in Vranje, Serbia

- accommodation of 3 project team members staying in Vranje for 3 nights in a 2 or 3 star hotel (single rooms, including breakfast);

- 5-day Development of the models for the new “Train-the-Trainer” curricula event in Vranje, Serbia

- accommodation of 1 project team member in Vranje for 5 nights in a 2 or 3 star hotel (single rooms, including breakfast).

- Consumables for following events:

- 3-day entrepreneurial learning programme development session – 43 persons

- Flipchart pads – 5 pcs,

- Permanent markers (4 different colors set) – 3 pcs,

- Notebooks, A4 – 45 pcs

- Pens – min 43 pcs.

- Folder Pockets, A4 – 50 pcs.

- PVC file folders with perforation, A4 – 20 pcs.

- Ring binders, 8cm – 5 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 2 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 1 ream

- 6-months Entrepreneurial learning course for elementary schools – 60 students, 96 classes

- Flipchart pads – 30 pcs,

- Permanent markers (4 different colors set) – 20 pcs,

- Notebooks, A4 – 80 pcs.

- Pens – min 300 pcs.

- Test materials – min. 70 printed copies

- Satisfaction questionnaires, developed under the project activity – min. 70 printed copies

- Folder Pockets, A4 – 200 pcs.

- PVC file folders with perforation, A4 – 50 pcs.

- Ring binders, 8cm – 15 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 5 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 10 reams

- USB flash drives 2.0, 8GB – 65 pcs.

- 6-months Entrepreneurial learning course for secondary schools – 30 students, 120 classes

- Flipchart pads – 40 pcs,

- Permanent markers (4 different colors set) – 25 pcs,

- Notebooks, A4 – min 60 pcs.

- Pens – min 200 pcs.

- Test materials – min. 40 printed copies

- Satisfaction questionnaires, developed under the project activity – min. 40 printed copies

- Folder Pockets, A4 – 150 pcs.

- PVC file folders with perforation, A4 – 50 pcs.

- Ring binders, 8cm – 15 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 5 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 10 reams

- USB flash drives 2.0, 8GB – 35 pcs.

- 4-months Train-the-Trainer course implementation – 23 students, 96 classes

- Flipchart pads – 30 pcs,

- Permanent markers (4 different colors set) – 20 pcs,

- Notebooks, A4 – 30 pcs.

- Pens – min 100 pcs.

- Test materials – min. 30 printed copies

- Satisfaction questionnaires, developed under the project activity – min. 30 printed copies

- Folder Pockets, A4 – 100 pcs.

- PVC file folders with perforation, A4 – 50 pcs.

- Ring binders, 8cm – 10 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 4 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 6 reams

- USB flash drives 2.0, 8GB – 28 pcs.

- Students companies development activity – 90 students, 30 classes

- Flipchart pads – 15 pcs,

- Permanent markers (4 different colors set) – 10 pcs,

- Notebooks, A4 – min 100 pcs.

- Pens – min 200 pcs.

- Folder Pockets, A4 – 100 pcs.

- PVC file folders with perforation, A4 – 50 pcs.

- Ring binders, 8cm – 10 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 2 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 6 reams

- USB flash drives 2.0, 8GB – 95 pcs.

- 5-days Entrepreneurial learning curricula session – 37 participants

- Flipchart pads – 7 pcs,

- Permanent markers (4 different colors set) – 3 pcs,

- Notebooks, A4 – min 40 pcs.

- Pens – min 80 pcs.

- Folder Pockets, A4 – 80 pcs.

- PVC file folders with perforation, A4 – 25 pcs.

- Ring binders, 8cm – 5 pcs

- Cardboard dividers, 5 colors, 25 pcs pack – 1 packages

- Universal office paper, A4, 80g.m2, 500 sheets/ream – 1 ream

Consumable to be used for all above events – 1 laser printer print head for printing questionnaires, test materials and other documents for the events.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

Responsible body for this service contract will be the Contracting Authority specified above.

### Management structure

The Contracting Authority International Business School, Botevgrad, Republic of Bulgaria and in its capacity it is responsible for conducting the current service tender procedure, signing the service contract and carrying out the overall control on the contract implementation. The day-to-day operational project implementation will be also performed by the International Business School, Botevgrad and the project team – which is responsible for implementation of project No. CB007.1.21.159: “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”; Priority Axis: Youth; Specific Objective 2.1 Skills and Entrepreneurship; Type of project: Soft, financed by the European Union, in accordance with the rules of Interreg – IPA CBC Bulgaria – Serbia Programme CCI Number 2014TC16I5CB007.

### Facilities to be provided by the Contracting Authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The operational base for the project will be set up in Botevgrad, Bulgaria. The events will take place on the cross-border territory of Bulgaria and Serbia according to 4.1.

## Start date & Period of implementation of tasks

The intended start date is 03.10.2017 and the period of implementation of the contract will be 5 months from this date, and not later than 22.02.2018. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language:

- Draft final report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 days after receipt of comments on the draft final report. This report should provide conclusions and clear evidences on the implementation of all requested services. The final report must be provided along with the corresponding invoice.

The reports provided by the Contractor should be prepared in English language and submitted in the following copies:

- 1 (one) original, duly signed, stamped and dated by the legal representative of the Contractor and

- 1 (one) electronic version.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicators are specified as related to each type of services, to be provided:

- Rented of 2 halls - for one 430 participants 1-day event and for one 245 participants 1-day event;

- Rented and provided audio/video equipment for one 430 participants 1-day event and for one 245 participants 1-day event;

- Provided Catering services for the following events:

- 3-day entrepreneurial learning programme development session – 35 persons;

- 1-day Joint Classes Day for elementary schools – 141 persons;

- 1-day Joint Classes Day for secondary schools – 67 persons;

- 1-day Cooperation with parents event - 422 participants

- 5-days Entrepreneurial learning curricula session – 35 persons

- 1- day BOND Conclusion event - 237 participants

- Provided Refreshment for 7 university students for 2 weeks;

- Provided transportation of the participants in the following events:

- 113 Bulgarian participants to/from the BOND outset event in Vranje, Serbia;

- local travels of 13 teachers for the 3-day session in Botevgrad, Bulgaria;

- travel of 23 participants to/from 3-day session in Vranje, Serbia;

- travel of 23 participants to/from 1-day Joint Classes day in Vranje, Serbia;

- travel of 23 participants to/from 3-day session in Vranje, Serbia;

- local travels of max. 203 participants of 1-day Cooperation with parents event in Botevgrad, Bulgaria;

- transport 203 participants to/from the 1-day Students BOND Day in Vranje, Serbia;

- travels of 14 participants to/from the 5-day session in Vranje, Serbia;

- local travels of max. 113 participants for Closing event in Botevgrad, Bulgaria;

- Accommodation for participants in the following events:

- 3-day “Train-the-Trainer”programme elaboration event in Vranje, Serbia - 23 participants staying in Vranje for 3 nights

- 3-day Exchange of practice event in Vranje, Serbia - accommodation of 23 participants staying in Vranje for 3 nights

- 5-day Development of the models for the new “Train-the-Trainer” curricula event in Vranje, Serbia - 14 participants staying in Vranje for 5 nights.

- Accommodation for project team members in the following events:

- 3-day “Train-the-Trainer”programme elaboration event in Vranje, Serbia - 3 project team members staying in Vranje for 3 nights;

- 3-day Exchange of practice event in Vranje, Serbia - 3 project team members staying in Vranje for 3 nights;

- 5-day Development of the models for the new “Train-the-Trainer” curricula event in Vranje, Serbia - 1 project team member in Vranje for 5 nights.

- Consumables for following events:

- 3-day entrepreneurial learning programme development session – 43 persons

- 6-months Entrepreneurial learning course for elementary schools – 60 students, 96 classes

- 6-months Entrepreneurial learning course for secondary schools – 30 students, 120 classes

- 4-months Train-the-Trainer course implementation – 23 students, 96 classes

- Students companies development activity – 90 students, 30 classes

- 5-days Entrepreneurial learning curricula session – 37 participants

## Special requirements

N/A