|  | Interreg – IPA CBC Bulgaria – Serbia Programme CCI Number 2014TC16I5CB007 |  |
| --- | --- | --- |

Project No 2014TC16I5CB007-2015-1-124: Conservation, revitalization and exhibition of Early Christian basilica and medieval fortress in cross border region

VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Communications between the Contracting Authority and/or the Supervisor on the one hand, and the Contractor on the other, shall be exclusively in writing. Official communications shall be sent by post or delivered by hand to the following addresses:

For the Contracting Authority:

- Contact person: Mr Deyan Dimitrov

City of Montana, 1 Izvora Str.

City of Montana 3400

Bulgaria

- Tel: +359 96 394 262, Fax: +359 96 300 462

E-mail address: montana@montana.bg

For the Contractor:

…………………………………………

………………………………………….

…………………………….,

tel./fax: …………………..; e-mail: ………………………….

Unofficial communication will be exchanged by phone, e-mail or fax transmission,

The correspondence between the Contractor and the Supervisor shall be done according to the prescriptions in the Bulgarian Law of Spatial planning and all relevant Regulations. Copies of the administrative orders and all other documentation exchanged between both parties shall be presented to the Contracting Authority as well

Article 5	Supervisor and Supervisor’s representative

5.2	The project site supervisor and its representatives will be assigned by the Contracting Authority in another contract.

5.3	The project site supervisor and its representatives have the powers and responsibilities described in the Bulgarian Law on Spatial Planning.

5.4	Instructions and/or orders issued in writing by the Supervisor shall be made in the compliance with Bulgarian Law on Spatial Planning in the order book of the construction

Article 8	Documents to be provided

8.1	Within 10 days of the signing of the contract, the Contracting Authority in Supervisor’s presents shall provide the Contractor, free of charge, with a copy of the drawings prepared for the implementation of the contract and a copy of the specifications and other contract documents. Upon the issue of the final acceptance, the Contractor shall return to the Contracting Authority all drawings, specifications and other contract documents.

8.2 	If a Party becomes aware of any mistake or fault of technical nature in a document that has been prepared to be used for the execution of the works on site, the Party must send notice to the other Party, notifying of such a mistake or fault

Article 9	Access to the site

9.1	The Contracting Authority shall, in 30 days of contract signature and in conformity with the progress of the works, place the site and access thereto at the disposal of the Contractor in accordance with the approved programme of implementation of tasks and in conformity with national legislation/ Art. 157 (1) of the Bulgarian Law of Spatial planning/. During the construction works the Contractor shall provide an appropriate access to other persons such as representatives of the Contracting Authority, Site Supervisor, Audit and Control authorities.

Article 12	General Obligations

12.9	The visibility activities must comply with the rules lay down in the Communication and Visibility Manual for EU External Actions published by the European Commission.

Article 12c	Design and build contracts

12c1	N/A

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 5 % of the amount of the Contract and any addenda thereto.

15.8	Within 45 days after the deliverance of the certificate of provisional acceptance according to article 60.1 and the completion of any outstanding work or reservation, 100 % of the amount of the performance guarantee may be released.

Article 16	Liabilities and Insurance

16.2	The Contractor shall establish a general insurance policy covering the third party risks in accordance with Art. 171 of the Bulgarian Law of Spatial planning or equivalent, covering the minimum insurance amount according to Bulgarian Ordinance of the terms and conditions of mandatory insurance in design and construction issued in the State Gazette on March 2004. .

16.4. All the insurance referred to this Article shall be taken out with the Contract signature. The Contractor should submit copies of the insurances to the Contracting Authority, for information.

Article 17	Programme of implementation of tasks

If there is a change in the work programme submitted as part of the offer, the Contractor shall provide the Supervisor and the Contracting authority with a new programme of implementation of the tasks, broken down by activity and by month within 3 days of finding a necessity to update the programme

Article 19	Contractor’s drawings and execution studies

19.1	N/A

19.7	Before provisional acceptance of the works, the Contractor shall supply operation and maintenance manuals together, which shall be in such detail as will enable the Contracting Authority to operate, maintain, adjust and repair all parts of the works. The manuals and drawings shall be in the language of the contract or in Bulgarian. The works shall not be considered to be completed for the purpose of provisional acceptance until such manuals and drawings have been supplied to the Contracting Authority.

Article 20	Sufficiency of tender prices

No derogation from General conditions

Article 21	Exceptional risks

21.4	No derogation from General conditions

Article 24	Interference with traffic

24.1	The Contractor shall ensure that the works and installations do not cause damage to, or obstruct traffic on, communication links such as roads, waterways and electric ways. The organization of the site of construction shall be made in accordance to the detailed design drawings part of this contract.

24.2	Any special measures assigned in the detailed design drawings part of this contract in order to protect or strengthen existing infrastructure, shall be at the expense of the Contractor. The Contractor shall inform the Supervisor of any special measures it intends to take before carrying them out. The repair of any damage caused to existing infrastructure by the transport of materials, plant or equipment shall be at the expense of the Contractor.

Article 27	Demolished materials

27.2	Any demolition work, materials and articles obtained therefrom suitable for further use shall become the property of the Contracting Authority. Such materials shall be provided to the disposal of the Contracting Authority, which is responsible for their transportation and further storage of useful materials.

27.4	The Contracting Authority is responsible for the transportation and further storage of demolition work, materials and articles suitable for further use. The Contractor shall, at its expense, progressively remove rubble and other demolition materials, rubbish and debris which are not useful from the site of construction

Article 29	Temporary works

29.2	No derogation from General conditions

Article 30	Soil studies

30.1	No derogation from General conditions

Article 32	Patents and licenses

32.1	No derogation from General conditions

Article 34	Period of implementation of tasks

34.1	The time for completion of the construction works is 9 /nine/ months from the date of providing access to the Site.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1	An order book and acts and protocols in the construction process will be kept on the site by the Contractor and shall be developed and signed by the Supervisor, who shall enter in it all information in accordance to the Bulgarian Law of Spatial planning.

39.2	The statements shall form an integral part of the work register but may, where appropriate, be recorded in separate documents. The statements for work registration will be complied by the Contractor and will be approved by the Supervisor at the same time.

Article 40	Origin and quality of works and materials

## 40.1	All goods purchased under the Contract must originate in any eligible source country as defined in of IPA Cross-border programme. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

When importing goods, any change in the specified origin must be pointed out to the project Supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with Bulgarian standards and codes and the Technical specifications, volume 3, part of the Contract.

## Article 41	Inspection and testing

No derogation from General conditions

Article 43	Ownership of plant and materials

43.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the Contracting Authority.

Article 44:	General principles for payments

44.1	Payments shall be made in BGN. The conversion into euro of the real costs borne in national currency shall be done at the fixed rate of Bulgarian National Bank (1 euro=1.95583 BGN).

44.3   By derogation, pre-financing payment to the Contractor shall be made within 20 days.  By derogation the payment to the Contractor of the amounts due under each of the interim payment certificates and the final statement of account issued by the Supervisor shall be made by the Contracting Authority within 20 days.

Article 46	Pre-financing

46.1	A pre-financing will be granted to the Contractor, at its request and before the first interim payment takes place as a lump-sum advance enabling it to meet expenditure resulting from the commencement of the contract;

46.2	The amount of the pre-financing is 20% of the original contract price.

46.3(c)	By derogation to article 46.3(c) no pre-financing guarantee is required.

46.8	Repayment of the pre-financing shall take the form of deductions based on monthly claims. No exceeds of 10% of the certified amount shall be deducted from each Interim Certificate for the repayment of the pre-financing until the pre-financing is fully repaid.

Article 47	Retention monies

Not applicable

Article 48	Price revision

Not applicable

Article 49	Measurement

49.1	This is a unit-price contract.

49.1 iii)	No additions shall be made to the items in the Bill of Quantities except as a result of a modification in accordance with Article 37 of General Conditions.

49.1 iv)	The Supervisor will control permanently the implementation of the works and their accordance with the quantities and quality of the materials laid down in the contract, also he will control the implementation according the requirements of the Bulgarian legislation and Article 49 of the General Conditions. The arrangements for measuring shall be in compliance with the Bulgarian Law of Spatial planning and relevant Regulations.

Article 50	Interim payments

50.1	The Contractor shall submit an Interim Certificate to the Contracting Authority at the end of each month, in a form presented by the Contracting Authority. The Contractor shall issue an Interim Certificate only if the total amount of the Interim certificate is at amount not less than 10% of the Contract price. The Interim Certificates should be approved by the Supervisor prior submission to Contracting Authority and to include the items, as applicable, state in article 50.1 of the General Conditions.

Article 51	Final statement of account

51.1	The Contractor shall, submit to the Supervisor a draft final statement of account when it applies for the provisional acceptance certificate. In order to enable the Supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the Contractor considers to be due to it under the contract.

51.2	Within 30 days from issuing the certificate of final acceptance referred to in article 62, the Supervisor shall prepare and signed the final statement of account.

Article 53	Delayed payments

53.1	By derogation from Article 53.1 of the General Conditions, once the time-limit referred Article 44.3 has expired, the Contractor shall be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions.

However, when the interest calculated in accordance with the first subparagraph is lower than or equal to EUR 200, it shall be paid to the creditor only upon a demand submitted within two months of receiving late payment.

Article 59	Partial acceptance

59.3	In the cases of partial provisional acceptance referred to in Article 59.2 the defects liability period provided for in Article 61 shall run as from the date of such partial provisional acceptance.

Article 60	Provisional acceptance

60.1	The “certificate of provisional acceptance” is according to the National legislation for the construction works of the Contracting Authority (“Act 15” according to Article 176 of Bulgarian Law of Spatial planning and relevant Regulations).

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.7	The defects liability period shall be up in compliance with Article 20 from Bulgarian Ordinance № 2 dated 31 July 2003 for the commissioning of the construction in Republic of Bulgaria and warranty periods for completed construction works, facilities and construction sites.

The defects liability period shall commence on the date of provisional acceptance and may recommence in accordance with Article 61.2.

Article 62	Final acceptance

The “final acceptance certificate” is according to the National legislation for the construction works of the Contracting Authority (“Use permit” according to Bulgarian Law of Spatial planning, articles 177 and 178, and relevant Regulations).

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of competent Bulgarian court in accordance with the national legislation of the state of the Contracting Authority.

Article 72	Data Protection

Not applicable.

Article 73	Further additional clauses

Not applicable.

* * *