VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

  - Contracting authority: City of Pirot, LED office , Nenad Petrovic – project manager , nenad.petrovic @pirot.rs

Srpskih vladara 82, 18 300 Pirot ; Publication reference  2014TC16I5CB007-2015-1-124/LP-TD01

Reconstruction of medieval fortress " Kale" (upper and middle town and part of down   town)

Article 5	Supervisor and Supervisor’s representative

5.2	The power of the Supervisor and its representative is in compliance with Serbian legislation. The purpose of the service contract is the provision of Independent Construction Supervisor for the implementation of the construction works required by the project in compliance with Serbian legislation for Construction works (the provisions of the Law on planning and construction and all relevant Regulations). All representatives of supervisors will be appointed by Contracting Authority in compliance with Law on planning and construction. Written approval of Contracting Authority will be required whenever the Supervisor has to decide on quantity and/or quality of works, on any type of additional payment, and any extension of time or any other type of variation.

5.3	Any approval, inspection, certificate, examination, instruction, proposal, request, test or other similar action of the Supervisor shall not relieve the Contractor of any of his duties and responsibilities under this Contract, including responsibilities for any of his mistakes, faults or discrepancies. The Contractor must ensure that the Supervisor has free access to the facility and all the documentation relevant to the implementation of the current contract and the works herein. The Supervisor shall have access to all materials or items to be installed on the sites before they are actually fixed in place.

5.4	Instructions and/or orders issued by the Supervisor/ shall be by way of administrative orders and must be in compliance the Law on planning and construction. All administrative order by the Supervisor shall be issued in three copies, one for the Supervisor, one for the Contracting Authority and one for the Contractor.

Article 7	Subcontracting

7.3	The upper limit authorized for subcontracting is 30% of the Contract Price.

Article 8	Documents to be provided

To replace sub article 8.1 with the following:

  - Within 15 days of the signing of the contract, the Contracting Authority and Supervisor’s representatives shall provide the Contractor, free of charge, with a copy of the drawings prepared for the implementation of the contract and a copy of the specifications and other contract documents. Upon the issue of the final acceptance, the Contractor shall return to the Contracting Authority all drawings, specifications and other contract documents.

To replace e sub article 8.2 with the following:

  - If a Party becomes aware of any mistake or fault of technical nature in a document that has been prepared to be used for the execution of the works on site, the Party must send notice to the other Party, notifying of such a mistake or fault.

Article 9	Access to the site

9.1	The Contractor is reminded that there is a Head of Interreg IPA CBC Bulgaria-Serbia Programme  in the state of the Contracting Authority. The Contractor is obliged to give the Head Interreg IPA CBC Bulgaria-Serbia Programme free access to its sites, factories, workshops, etc., and generally assist the Head Interreg IPA CBC Bulgaria-Serbia Programme  , like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the Head of Delegation.

Appendix to sub article 9.1 The Contracting Authority shall 15 days after signature of the Works contract give access of the Contractor to the Site in compliance with the Serbian Law on planning and construction.

Article 12	General Obligations

Replace sub article 12.9with the following:

  - The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: http://ec.europa.eu/europeaid/work/visibility/index_en.htm and http://www.ipacbc-bgrs.eu/news/updated-version-project-implementation-manual-under-first-call-proposals

After sub article 12.10 add sub article 12.11

12.11. The Contractor shall be responsible for the safekeeping of any formal documents relating to the works, according to Serbian Law of Planning and Construction.

Article 12c	Design and build contracts

After sub article 12c1 add sub article 12c2

Contractor shall deliver to Supervisor and Contracting authority the following :      Construction diary and Construction book. The declaration  on the responsible Contractor (odgovorni izvodjac radova) under Serbian Law on Planning and Construction.

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 7% of the amount of the Contract and any addenda thereto. The performance guarantee shall be released within 45 days of the issuing of the signed final statement of account for its total amount except for amounts which are the subject of amicable settlement, arbitration or litigation.

Article 16	Liabilities and Insurance

16.1 a)	No derogation from General Conditions.

16.1 b)	No derogation from General Conditions.

16.2 a)  point 4 	Tenderer must provide the relevant insurance for their workers.

Within 16.2.5 add  text:

Contractor has obligation to provide Insurance of liability related to the soundness of the works in accordance to Article 158 of Law on Planning and Construction of Serbia in terms of Warranty period.

Article 17	Programme of implementation of tasks

In case of any unforeseen circumstances or additional works , Contracting Authority must require approval from the Managing Authority

Article 19	Contractor’s drawings and execution studies

19.1	The Contractor shall submit Construction diary daily to the Supervisory authority to sign it. The Contractor will periodically submit construction book to the supervisory authority to sign it until the period of making the situations. Signing of the situations will be the basis for the procedure of payment to the Contractor.

In case of some unforeseen circumstance on the building site, contractor should make   detailed explanation  and submitted for the Supervisor’s approval, if applicable

19.7	Language of the manuals and drawings is language of the Contract. but also should be translated in Serbian

Article 20	Sufficiency of tender prices

No derogation from General conditions

Article 21	Exceptional risks

21.4	No derogation from General conditions

Article 24	Interference with traffic

24.1	/

24.2	The Contractor shall be responsible for providing all permits necessary for performing the works described in this Article including declarations of public companies and other institutions responsible for cultural facilities of special importance.

Add following articles after Article 24.2:

24.3	No important operation of any kind, especially cutting through, transit over, or closing existing roads, water conduits or other public utility shall be carried out without the written consent of the Supervisor.

24.4   The Contractor shall inform the Supervisor in due time which shall be not less than 7 calendar days in writing before commencing such works in order that the Supervisor may arrange adequate supervision and safety precautions. With his application for permission to start construction work, the Contractor shall submit to the Supervisor a list of all major plant he and his sub-contractors intend to use, indicating their characteristics.

Article 27	Demolished materials

27.2	Demolition materials are the property of the Contracting Authority in accordance to Technical specification and work description for this contract

27.4	The Contractor is obligated to remove demolition material.

Article 29	Temporary works

29.2	/

Article 30	Soil studies

30.1	In accordance to General conditions

Article 32	Patents and licenses

  - There is no derogation from Article 32 of the GC.

Article 33   Commencement order

Replace text of sub article 33.1 with the following:

33.1 The commencement date of the construction works is the date of giving access to the Site (according to Art. 148 of the Serbian Law on planning and construction i.e.  the introduction of contractors in the works contract which is evidenced in Construction  Log by supervisor.

Article 34	Period of implementation of tasks

34.1	Period of implementation of all tasks is 15 (fifteen) months from the commencement date.

Article 36	Delays in the implementation of tasks

36.1	In case of exceeding the deadline, Contractor is committed to pay for each day of delay to Contracting Authority 0,5‰ of the total contract value and not more than 5%. Completed situation for implemented works is permanently reduced by the amount of calculated contractual fine.

Article 39	Work register

Replace text of sub article 39.1 with the following:

39.1	A work register shall, be kept on the site by the Contractor. Work register at least will contain the following information:

- the weather conditions, interruptions of work owing to inclement weather, hours of work, number and type of workmen employed on the site, materials supplied, equipment in use, equipment not in working order, tests carried out in situ, samples dispatched, unforeseen circumstances, as well as orders given to the Contractor; This data will be in form of Construction Log (Građevinski dnevnik), according to Serbian Law of Planning and Construction.

- Detailed statements of all the quantitative and qualitative elements of the work done and the supplies delivered and used, capable of being checked on the site and relevant in calculating payments to be made to the Contractor.

39.2 Technical rules for drawing up statements should be in accordance with Serbian Law of Planning and Construction.

Article 40	Origin and quality of works and materials

- 40.1	All goods purchased under the Contract must originate in any eligible source country as defined in Interreg IPA  CBC Bulgaria-Serbia programme. However, the goods to be purchased may originate from any country, whenever the total price of the estimated quantity of those goods, as reflected in a separate item of the Breakdown of the Lump-sum Price (Volume 4.2.3) is below 100.000 €.

- A category of similar goods to be purchased shall not be broken down over more than 1 item of the: Breakdown of the Lump-sum Price (Volume 4.2.3)

## For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

When importing goods, any change in the specified origin must be pointed out to the project Supervisor and approved by him.

At the end of sub article 40.2 add following text:

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*)	The works and objects, equipment or materials used in their construction must comply as a         minimum with the Technical Specifications, volume 3, part of the Contract.

(*)	the requirements of Serbian standards and codes according to Serbian Law of Planning and Construction and Law on Cultural Assets of RS

40.3	Preliminary technical acceptance is  not necessary

Article 41	Inspection and testing

Any part on the reconstructed object can be inspected and tested Serbian Law of Planning and Construction -Article 153

Article 43	Ownership of plant and materials

43.2	Equipment, temporary structures, plant and materials on the site do not belong to the Contracting Authority under Article 43 of the General Conditions and the legal instrument(s) used.

Article 44:	General principles for payments

44.1	Payments shall be made in  euro (in case the Contractor is registered in the  country outside of Serbia) or  in RSD (in case the Contractor is registered in Serbia)   (equal in RSD in the currency exchange rate of the Infor Euro at the month of launching the tender shall be used))

44.2	Sub section is replaced with

Payments due by the Contracting Authority shall be made to the bank account mentioned on the financial identification form completed by the Contractor. The same form, annexed to the payment request must be used to report changes of bank account in payment procedure

44.3	By derogation, Interim payments to the Contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 45 days by Contracting authority . and the final payment to the Contractor of the amounts due after the final statement of account issued by the Supervisor shall be made within 30 days from the day of final statement account.

Payments shall be made in EUR/RSD  according to the following schedule:

- First Interim payment 30%, upon submission of necessary documents regarding First temporary situation (prva privremena  situacija)  with approval of Supervisor  as a proof of performed works  - 4 months from the commencement day

- Second Interim payment 30%, upon submission of necessary documents regarding Second temporary situation (druga privremena  situacija)  with approval of Supervisor  as a proof of performed works  - 5 months from the commencement day

- Final payment 40% after the positive technical acceptance of works, supervisor approval  and issuing of final acceptance-6 months from the commencement day

- Payments will be authorised and made by City of Pirot , Srpskih vladara 82  , 18300 Pirot, which is represented by Vladan Vasic, the Mayor.

Article 46	Pre-financing

46.1	Pre-financing is not possible.

46.2	Not applicable

46.3(c)	/

46.8	/

Article 47	Retention monies

47.1	Not applicable

Article 48	Price revision

Price revision is not allowed by any circumstances.

Article 49	Measurement

49.1

(*)	This is a lump-sum contract.. It will be will be defined on the base of construction book by measuring the material used in  construction works.

Article 50	Interim payments

50.1	In order to obtain interim payment the Contractor must forward to the Contracting Authority referred to paragraph 44.3, the payment request and provisional situation on finished works signed by Supervisor. Interim payment shall be previously checked and signed by the Supervisor.

Article 51	Final statement of account

51.1	The Contractor shall, submit to the Supervisor a draft final statement of account when it applies for the provisional acceptance certificate. In order to enable the Supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the Contractor considers to be due to it under the contract.

51.2	Within 7 days from issuing the certificate of final acceptance referred to in article 62, the Supervisor shall prepare and signed the final statement of account.

Article 57 General principles

Article 60	Provisional acceptance

60.1	In complement to article 60.1 of the General Conditions Provisional acceptance will be organized when 100% of contracted work is finished. No partial acceptance will be allowed.

60.2 	In complement to article 60.2 of the General Condition, the Supervisor shall within 5 days after the receipt of the Contractors’s application either

- issue the certificate of provisional acceptance to the Contractor with a copy to the

Contracting Authority stating, where appropriate, his reservations, and, inter alia,

the date on which, in his opinion, the works were completed in accordance with the

contract and ready for provisional acceptance; or

b)   reject the application giving his reasons and specifying the action which, in his

opinion, is required of the Contractor for the certificate to be issued.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.7	Duration of the defects liability period is max 30 days.

Article 62: 	Final acceptance

After sub article 62.3 add sub article 62.4:

62.4	The “final acceptance certificate” will be issued only after positive certificate on acceptance of works (“Zapisnik o tehnickom prijemu or Zapisnik o primopredaji radova) is issued, if all the works are truly completed and in accordance with requirements of this Contract.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of  Economic Court Nis Serbia in accordance with the national legislation of the state of the Contracting Authority.

Article 72	Data Protection

Not applicable.]

Article 73	Further additional clauses

Not applicable

* * *