Project N CB007.1.11.349: Creating preconditions for better accessibility to touristic attractions in Pantelej and Lom by improving the touristic infrastructure and increasing the number of tourists;.

VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Communications between the Contracting Authority and/or the Supervisor on the one hand, and the Contractor on the other, shall be exclusively in writing. Official communications shall be sent by post or delivered by hand to the following addresses:

For the Contracting Authority:

Contact person: Nataliya Stefanova

- Municipality of Lom, Republic of Bulgaria,

- Address 12 Dunavska Str., 3600 Town of Lom

- Tel: +359 971 69 101

- Fax: +359 971 66 026

e-mail address: lom.municipality@lom.egov.bg

For the Contractor:

…………………………………………

………………………………………….

…………………………

…………………………….,

tel./fax: …………………..; e-mail: ………………………….

Article 5	Supervisor and Supervisor’s representative

5.2	The project site supervisor and its representatives will be assigned by the Contracting Authority in another contract.

5.3	The project site supervisor and its representatives have the powers and responsibilities described in the Bulgarian Law on Spatial Planning.

5.4	Instructions and/or orders issued in writing by the Supervisor shall be made in the compliance with Bulgarian Law on Spatial Planning in the order book of the construction

Article 9	Access to the site

9.1	The Contracting Authority shall, in 30 days of contract signature and in conformity with the progress of the works, place the site and access thereto at the disposal of the Contractor in accordance with the approved programme of implementation of tasks and in conformity with national legislation/ Art. 157 (1) of the Bulgarian Law of Spatial planning/. During the construction works the Contractor shall provide an appropriate access to other persons such as representatives of the Contracting Authority, Site Supervisor, Audit and Control authorities.

Article 12	General Obligations

12.9	The visibility activities must comply with the rules lay down in the Communication and Visibility Manual for EU External Actions published by the European Commission.

Article 15	Performance guarantee

15.1	By derogation to Article 15 of the General Conditions, no performance guarantee is required under this contract.

Article 16	Liabilities and Insurance

16.1.	The Contractor shall establish a general insurance policy covering the third party risks in   accordance with Art. 171 of the Bulgarian Law of Spatial planning or equivalent, covering the minimum insurance amount according to Bulgarian Ordinance of the terms and conditions of mandatory insurance in design and construction issued in the State Gazette on March 2004. .

16.2.	The amount of insurance covering liability with regard to risks and civil liability insurance shall be in accordance with article 5, paragraph 2, section 5 of the Bulgarian Ordinance of the terms and conditions of mandatory insurance in design and construction issued in the State Gazette on March 2004.

Article 17	Programme of implementation of tasks

17.1	The Contractor shall provide the Supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the Contractor proposes to carry out the works, and shall be based on the tranches foreseen in art. 49.1 of the special conditions.

17.2. 	The Supervisor shall return this document to the Contractor with any relevant remarks within 10 days of receipt, save where the Supervisor, within those 10 days, notifies the Contractor of its wish for a meeting in order to discuss the documents submitted.

Article 21	Exceptional risks

21.4	      No derogation from General conditions

Article 34	Period of implementation of tasks

34.1	The time for completion of the construction works is 10 /ten/ months from the date of providing access to the Site.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1	 An order book and acts and protocols in the construction process will be kept on the site by the Contractor and shall be developed and signed by the Supervisor, who shall enter in it all information in accordance to the Bulgarian Law of Spatial planning.

39.2	The statements shall form an integral part of the work register but may, where appropriate, be recorded in separate documents. The statements for work registration will be complied by the Contractor and will be approved by the Supervisor at the same time.

Article 40	Origin and quality of works and materials

## 40.1	All goods purchased under the Contract must originate in any eligible source country as defined in IPA Cross-border programme. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

When importing goods, any change in the specified origin must be pointed out to the project Supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with Bulgarian standards and codes and the Technical specifications, volume 3, part of the Contract.

Article 43	Ownership of plant and materials

43.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the Contracting Authority.

Article 44:	General principles for payments

44.1	Payments shall be made in BGN. The conversion into euro of the real costs borne in national currency shall be done at the fixed rate of Bulgarian National Bank (1 euro=1.95583 BGN).

44.3	Payments to the Contractor shall be done as follows:

a. 	By derogation, pre-financing payments shall be made within 30 days of receipt by the Contracting Authority of the Contractor’s invoice. The date of payment shall be the date on which the paying account is debited.

b. 	By derogation, payments to the Contractor of the amounts due under each of the interim payment certificates and final statement of account issued by the Supervisor shall be made within 60 days of such certificate of statement accompanied by the Contractor’s invoice being delivered to the Contracting Authority. The date of payment shall be the date on which the paying account is debited.

Article 46	Pre-financing

46.1	The only prefinancing granted to the Contractor, is the lump sum advance referred to in Article 46.1(a).

46.2	By derogation to Article 46.2 of the General Conditions, the lump sum advance referred to in Article 46.1(a) shall be 20% of the original contract price.

46.3(c)	By derogation to Article 46.3(c) of the General Conditions, no pre-financing guarantee is required.

46.8	The tranches laid down in Article 49.1 of these Special Conditions are determined so that the pre-financing is fully repaid before Provisional Acceptance.

Article 47	Retention monies

47.1	The sum retained to guarantee implementation of the Contractor’s obligations during the defects liability period is 10 % of the contract price. By derogation to Article 47.1 of the General Conditions, that money is not retained from interim payments. The tranches laid down in Article 49.1 of these Special Conditions are determined so that the retention sum amounts to 10% of the contract price at the moment of the Certificate of provisional acceptance.

47.2	By derogation to Article 47.2 of the General Conditions, the retention sums can not be substituted by a retention guarantee.

Article 48	Price revision

48.1	Prices are fixed and shall not be revised.

Article 49	Measurement

49.1	This is a lump-sum contract.

Under the conditions imposed by the Special Conditions and General Conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 20% | Lump-sum advance of Article 46.1(a) | After conclusion of the contract |
| 2. | 20% | Interim payment of Article 50 | After completion of 40% of the firm quantities for which the Contractor submitted its all-in price. |
| 3. | 20% | Interim payment of Article 50 | After completion of 60% of the firm quantities for which the Contractor submitted its all-in price] |
| 4 | 30% | Interim payment of Article 50 | After issuing of the Certificate of provisional acceptance (Act 15 for the construction, according to applicable national legislation for construction works). |
| <last> | 10% | Retention money of Article 47 | Within 45 days of the issuing of the signed Final statement of account (Permission to use the building for the construction, according to applicable national legislation for construction works). |

Article 50	Interim payments

50.7	The interim payments will be paid as determined in Article 49.1 of these Special Conditions.

Article 53	Delayed payments

53.1	By derogation from Article 53.1 of the General Conditions, once the time-limit referred Article 44.3 has expired, the Contractor shall be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions.

However, when the interest calculated in accordance with the first subparagraph is lower than or equal to EUR 200, it shall be paid to the creditor only upon a demand submitted within two months of receiving late payment

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance (according to applicable national legislation for construction works), during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.2	The defects liability period shall be up in compliance with Bulgarian Ordinance № 2 dated 31 July 2003 for the commissioning of the construction in Republic of Bulgaria and warranty periods for completed construction works, facilities and construction sites.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of competent Bulgarian court in accordance with the national legislation of the state of the Contracting Authority.

Article 72	Data Protection

Not applicable.

* * *